	RKA ASSOCIATES
Construction Claims and Commercial Management
	EXTENSION OF TIME CLAIM
FIDIC 2017  ·  Sub-Clause 8.5



CLAIM DETAILS
	Project
	[Project name]
	Claim reference
	[EOT-001]

	Contract
	[e.g. FIDIC Red Book 2017]
	Date submitted
	[DD/MM/YYYY]

	Related Notice of Claim
	[Ref and date]
	Current Time for Completion
	[DD/MM/YYYY]

	From (Contractor)
	[Organisation and name]
	To (Engineer)
	[Organisation and name]


Guidance: under Sub-Clause 8.5 (2017 editions; 8.4 in the 1999 editions) the Contractor is entitled to an extension of the Time for Completion where completion is or will be delayed by a listed cause, including Variations, exceptionally adverse climatic conditions, unforeseeable shortages, and delay or impediment caused by the Employer or Employer’s Personnel. The claim is made in accordance with Sub-Clause 20.2, so the 28 day Notice of Claim and 84 day fully detailed claim time limits apply.
CAUSE OF DELAY
	[Identify the cause of delay and the Sub-Clause 8.5 limb or other Sub-Clause relied on. Describe the delaying event and how it affected the critical path.]







DELAY ANALYSIS
	Method of analysis
	[e.g. time impact / windows analysis]

	Baseline / current programme reference
	[Programme ref and date]

	Activities on the critical path affected
	[Activities]

	Delay to Time for Completion
	[calendar days]

	Revised Time for Completion sought
	[DD/MM/YYYY]


Guidance: attach the programme analysis demonstrating the effect on the critical path. Concurrency, mitigation and the quality of the supporting records are usually where EOT claims are won or lost.
SUPPORTING RECORDS ATTACHED
	[Programmes, progress records, site diaries, weather records, correspondence and instructions relied on.]





SIGNATURE
	Signed
	
	Signed
	

	Name
	
	Name
	

	For (Contractor)
	
	For (Engineer – acknowledgement)
	

	Date
	
	Date
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Free template for general guidance only. It is not legal or contractual advice and does not reproduce any published form of contract. Always check the clause references, notice periods and formalities in your own contract before use.
