| RKA ASSOCIATES Construction Claims and Commercial Management | NOTICE OF CLAIM FIDIC 2017 · Sub-Clause 20.2.1 |
| --- | --- |

NOTICE DETAILS

| Project | [Project name] | Claim reference | [CLM-001] |
| --- | --- | --- | --- |
| Contract | [e.g. FIDIC Red Book 2017 as amended] | Date of notice | [DD/MM/YYYY] |
| From | [Organisation and name] | To (Engineer / Employer) | [Organisation and name] |

Guidance: under Sub-Clause 20.2.1 of the 2017 editions the claiming Party gives a Notice of Claim describing the event or circumstance no later than 28 days after it became aware, or should have become aware, of the event or circumstance. Under Sub-Clause 20.2.2 a late notice means the claim is time barred, subject to the limited waiver procedure. Under the 1999 editions the equivalent notice is given under Sub-Clause 20.1. Check your Particular Conditions for amendments.

THE EVENT OR CIRCUMSTANCE

[Describe the event or circumstance giving rise to the claim. State what happened, when it occurred and when the claiming party became aware of it. At the notice stage a full statement of the contractual basis is not required, but the event must be identified clearly.]

NATURE OF THE CLAIM

|  | Extension of the Time for Completion |
| --- | --- |
|  | Additional payment / adjustment to the Contract Price |
|  | Both time and money |
|  | Other entitlement (state in the description) |

KEY DATES

| Date event occurred / commenced | [DD/MM/YYYY] |
| --- | --- |
| Date claiming party became aware | [DD/MM/YYYY] |
| 28 day notice deadline | [DD/MM/YYYY] |

Guidance: contemporary records should be kept from the date of this notice (Sub-Clause 20.2.3). The fully detailed Claim follows under Sub-Clause 20.2.4 within 84 days of awareness, or such other period as agreed or set in the Particular Conditions.

SIGNATURE

| Signed |  | Signed |  |
| --- | --- | --- | --- |
| Name |  | Name |  |
| For (claiming party) |  | For (Engineer / receiving party – acknowledgement) |  |
| Date |  | Date |  |