## Read me
RKA ASSOCIATES
NEC4 Contract Administration Registers
How to use this workbook
Enter your data in the yellow cells and in the rows below each header. White cells containing formulas update automatically.
Row 6 of each register contains a worked example showing the expected format. Overwrite or delete it once you add your own entries.
Status columns use dropdown lists. Pick from the list so the summary counts stay accurate.
Sheets in this workbook
CE Register | Log every compensation event from notification through quotation to implementation, with values and time effects.
Early Warning Register | The register required by clause 15. Record each matter, its potential effect and the actions agreed.
PMI Register | Track Project Manager's Instructions, whether the Scope changed and whether a compensation event was notified.
Free template from rkaassociates.com. For general guidance only, not legal or contractual advice. Check the clause references and procedures in your own contract.

## CE Register
RKA ASSOCIATES
Compensation Event Register
NEC4 ECC / ECS · clauses 60 to 66. Enter data in the rows below; the example in row 6 shows the format.
CE ref | Date notified | Notified by | Clause (60.1 ref) | Description | Status | Quotation due | Quotation value (£) | Implemented value (£) | Time effect (days) | Notes
CE-001 | 01/07/2026 | Contractor | 60.1(1) | PMI-003 revised outfall pipework to drawing C-201 rev B | Quotation submitted | 22/07/2026 | 18450 |  | 5 | Awaiting PM reply under cl 62.3
SUMMARY
Number of CEs logged | 1
Implemented | 0
Awaiting reply / open | 1
Total quotation value (£) | 18450
Total implemented value (£) | 0
Total time effect (days) | 5

## Early Warning Register
RKA ASSOCIATES
Early Warning Register
NEC4 clause 15. Keep this register current and review it at each early warning meeting.
EWN ref | Date raised | Raised by | Description of matter | Potential effect | Meeting date | Actions agreed | Owner | Status
EWN-001 | 24/06/2026 | Subcontractor | Long lead time on MCC panels risks energisation date | Delay Completion / Key Date 2 | 01/07/2026 | Contractor to review alternative supplier; update at next meeting | J Smith | Open
SUMMARY
Matters logged | 1
Open | 1
Closed | 0

## PMI Register
RKA ASSOCIATES
Project Manager's Instruction Register
NEC4 clause 14.3 / 27.3. Check every Scope-changing instruction has a CE notified under clause 61.1.
PMI ref | Date | Description | Changes Scope (Y/N) | CE notified (ref) | Quotation instructed (Y/N) | Status | Notes
PMI-001 | 15/06/2026 | Substitute handrail spec to Scope section 5.2 | Y | CE-002 | Y | Actioned | Quotation due 06/07/2026
SUMMARY
Instructions logged | 1
Scope changes | 1
With CE notified | 1